## Burndown Chart Template
Burndown Chart Template
Velocity = Total Story Points Delivered over a Sprint
The example below illustrates a basic example of a 4 Sprint Project. Being the Sprints in this case 2 weeks long this is a 2 month project.
It has 15 user stories in total. I've used the name "User Story #" in the essence of time, but you would of course write the actual user story using the format described in the other tab
Assumption: The team discards the user stories which aren't delivered
Sprint 1 |  | Story Points
customer can view menu |  | 6
admin can view products |  | 6
admin can add drinks |  | 5
customer can view profile |  | 3
| Total | 20 | Velocity Sprint 1 | 14
Sprint 2
admin can view orders |  | 4 |  | Note:diagrams were not completed in sprint 2 so were continued in sprint 3
diagrams |  | 6
customer can add to cart |  | 6
| Total | 16 | Velocity Sprint 2 | 16
Sprint 3
customer can login |  | 5
customer can signup |  | 5
diagrams |  | 1
| Total | 11 | Velocity Sprint 3 | 11
Sprint 4
customer can review products |  | 3 |  | Note: customer can review and admin can add customer were not completed in time
admin can login |  | 5
admin can add customers |  | 3
customer can add to cart |  | 5
customer can checkout |  | 5
| Total | 21 | Velocity Sprint 4 | 18
Total Story Points |  | 68 | Average Velocity | 14.75
Traditional
Burndown Chart
Sprint | Remaining Story Points
1 | 68
2 | 54
3 | 38
4 | 27